# Project Planning Phase

## Project Planning Template (Product Backlog, Sprint Planning, Stories, Storypoints)

Date: 15 February 2025
Team ID:LTVIP2026TMIDS91486
Project Name: HematoVision – Intelligent Blood Cell Classification System
Maximum Marks: 5 Marks

# Product Backlog, Sprint Schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| 🚀 Sprint-1 – Dataset & Preparation |  |  |  |  |  |  |
| Sprint-1 | Dataset Acquisition | USN-1 | Gathering blood cell image dataset | 3 | High |  |
| Sprint-1 | Dataset Acquisition | USN-2 | Organizing dataset into class folders | 2 | High |  |
| Sprint-1 | Dataset Acquisition | USN-3 | Loading dataset into ML environment | 1 | High |  |
| Sprint-1 | Data Preparation | USN-4 | Image resizing & normalization | 3 | High |  |
| Sprint-1 | Data Preparation | USN-5 | Applying data augmentation | 5 | Medium |  |
| Sprint-1 | Data Preparation | USN-6 | Splitting dataset (Train/Test) | 2 | High |  |
| 🚀 Sprint-2 – Model Development |  |  |  |  |  |  |
| Sprint-2 | Model Development | USN-7 | Loading pretrained CNN (MobileNetV2) | 2 | High |  |
| Sprint-2 | Model Development | USN-8 | Adding custom classification layers | 3 | High |  |
| Sprint-2 | Model Development | USN-9 | Compiling transfer learning model | 1 | High |  |
| Sprint-2 | Model Training | USN-10 | Training classification model | 5 | High |  |
| Sprint-2 | Model Evaluation | USN-11 | Evaluating accuracy & loss | 3 | High |  |
| Sprint-2 | Model Management | USN-12 | Saving trained model | 1 | High |  |
| 🚀 Sprint-3 – Prediction Pipeline |  |  |  |  |  |  |
| Sprint-3 | Prediction System | USN-13 | Implementing prediction logic | 3 | High |  |
| Sprint-3 | Prediction System | USN-14 | Displaying predicted cell type | 2 | High |  |
| Sprint-3 | Prediction System | USN-15 | Displaying confidence score | 2 | Medium |  |
| Sprint-3 | Error Handling | USN-16 | Handling invalid image inputs | 3 | High |  |
| Sprint-3 | Optimization | USN-17 | Improving inference speed | 5 | Low |  |
| 🚀 Sprint-4 – UI Integration & Refinement |  |  |  |  |  |  |
| Sprint-4 | UI Enhancement | USN-18 | Improving user interface design | 3 | Medium |  |
| Sprint-4 | UI Enhancement | USN-19 | Adding loading indicators | 2 | Medium |  |
| Sprint-4 | System Refinement | USN-20 | Improving result visualization | 3 | Medium |  |
| Sprint-4 | System Testing | USN-21 | End-to-end system testing | 5 | High |  |

# Project Tracker, Velocity & Burndown Data

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 18 | 6 Days | 15 Feb 2025 | 20 Feb 2025 | 18 | 20 Feb 2025 |
| Sprint-2 | 20 | 6 Days | 22 Feb 2025 | 27 Feb 2025 | 20 | 27 Feb 2025 |
| Sprint-3 | 16 | 6 Days | 01 Mar 2025 | 06 Mar 2025 | 16 | 06 Mar 2025 |
| Sprint-4 | 14 | 6 Days | 08 Mar 2025 | 13 Mar 2025 | 14 | 13 Mar 2025 |

# Velocity Calculation

Velocity = Total Story Points Completed / Number of Sprints

Total Story Points =
18 + 20 + 16 + 14 = 68

Number of Sprints = 4

Velocity =
68 / 4 = 17 Story Points per Sprint

# Average Velocity per Day

# Sprint Duration = 6 Days

Average Velocity per Day =
17 / 6 ≈ 2.8 Story Points per Day

Velocity Interpretation

Your team’s velocity is:

17 Story Points per Sprint

This indicates your team can reliably complete work worth ~17 story points every sprint.

# Burndown Chart Concept

Burndown Chart tracks:

✔ Work Remaining vs Time
✔ Sprint Progress
✔ Task Completion Rate

For HematoVision:

• Sprint begins with total story points
• Story points reduce as tasks complete
• Ends at zero when sprint completes